## Sheet1
S. No | Project/Client Name | Sent Date | Received Date | Estimation Time(Ahmed) | Estimated Budget(Ahmed) | Comments | Estimation Time(Leslie) | Estimated Budget(Leslie)
1 | GreenTech | 22-8-2013 | 24-8-2013 | 2-3 weeks | 750
2 | Orient | 22-8-2013 | 24-8-2013 | With Design : 15 Working Days Without Design: 10 Working Days | With Design : $750 Without Design: $450
3 | Somtel | 22-8-2013 |  |  |  | Questions from Ahmed
4 | Dahabshill | 22-8-2013 |  |  |  | Questions from Ahmed
5 | RAK | 24-8-2013 | 25-8-2013 | 3 Weeks | With Design : $800 Without Design: $550
6 | SSPEG | 24-8-2013 | 25-8-2013 | 3 Weeks | With Design : $800 Without Design: $550
7 | Duty Free | 24-8-2013 |  |  |  |  | 9 Weeks | AED 10000
8 | Orixcom | 26-8-2013
9 | Skylight | 26-8-2013 |  | With Design : 3 Weeks Without Design: 2 Weeks | With Design : $950 Without Design: $750
10 | Qatar Site Embassy | 28-8-2013 |  | With Design : 3 Weeks Without Design: 2 Weeks | With Design : $650 Without Design: $400
11 | Unique Properties | 28-8-2013 |  | 4 Weeks | 1100 |  | 7 Weeks | AED 5500